## Gantt Schedule
Project Schedule (Gantt Style)
Project | Task | Owner | Status | Start | End | Dur (wks) | Priority | W1 03/09 | W2 03/16 | W3 03/23 | W4 03/30 | W5 04/06 | W6 04/13 | W7 04/20 | W8 04/27 | W9 05/04 | W10 05/11 | W11 05/18 | W12 05/25 | W13 06/01 | W14 06/08 | W15 06/15 | W16 06/22 | W17 06/29 | W18 07/06 | W19 07/13 | W20 07/20 | W21 07/27 | W22 08/03 | W23 08/10 | W24 08/17 | W25 08/24 | W26 08/31
MH25004 JWMC Observation Bed | SD | Maryann / RDG | Active | 2026-03-09 | 2026-03-22 | 2 | Med
MH25004 JWMC Observation Bed | AHCA Stage I | Maryann / RDG | Pending | 2026-03-16 | 2026-03-22 | 1 | High
MH25004 JWMC Observation Bed | DD | Maryann / RDG | Pending | 2026-03-23 | 2026-04-05 | 2 | Med
MH25004 JWMC Observation Bed | CD | Maryann / RDG | Pending | 2026-03-30 | 2026-04-19 | 3 | Med
MH25004 JWMC Observation Bed | AHCA Stage III | Maryann / RDG | Pending | 2026-04-06 | 2026-04-12 | 1 | High
MH25004 JWMC Observation Bed | Permit/AHJ | Maryann / RDG | Pending | 2026-04-13 | 2026-05-10 | 4 | High
MH25019 JNMC Central Sterile | SD | Maryann / RDG | Pending | 2026-03-23 | 2026-04-05 | 2 | Med
MH25019 JNMC Central Sterile | DD | Maryann / RDG | Pending | 2026-03-30 | 2026-04-12 | 2 | Med
MH25019 JNMC Central Sterile | AHCA Stage II | Maryann / RDG | Pending | 2026-04-06 | 2026-04-12 | 1 | High
MH25019 JNMC Central Sterile | CD | Maryann / RDG | Pending | 2026-04-13 | 2026-05-03 | 3 | Med
MH25019 JNMC Central Sterile | AHCA Stage III | Maryann / RDG | Pending | 2026-04-20 | 2026-04-26 | 1 | High
MH25019 JNMC Central Sterile | Permit/AHJ | Maryann / RDG | Pending | 2026-04-27 | 2026-05-24 | 4 | High
MH25020 JNMC 3rd Floor ICU | SD | Maryann / RDG | Active | 2026-04-06 | 2026-04-19 | 2 | Med
MH25020 JNMC 3rd Floor ICU | DD | Maryann / RDG | Pending | 2026-04-13 | 2026-04-26 | 2 | Med
MH25020 JNMC 3rd Floor ICU | AHCA Stage II | Maryann / RDG | Pending | 2026-04-20 | 2026-04-26 | 1 | High
MH25020 JNMC 3rd Floor ICU | CD | Maryann / RDG | Pending | 2026-04-27 | 2026-05-17 | 3 | Med
MH25020 JNMC 3rd Floor ICU | AHCA Stage III | Maryann / RDG | Pending | 2026-05-04 | 2026-05-10 | 1 | High
MH25020 JNMC 3rd Floor ICU | Permit/AHJ | Maryann / RDG | Pending | 2026-05-11 | 2026-06-07 | 4 | High
MH25021 JNMC 5th Floor Enabling | SD | Maryann / RDG | Pending info | 2026-04-20 | 2026-05-03 | 2 | Med
MH25021 JNMC 5th Floor Enabling | DD | Maryann / RDG | Pending | 2026-04-27 | 2026-05-10 | 2 | Med
MH25021 JNMC 5th Floor Enabling | AHCA Stage II | Maryann / RDG | Pending | 2026-05-04 | 2026-05-10 | 1 | High
MH25021 JNMC 5th Floor Enabling | CD | Maryann / RDG | Pending | 2026-05-11 | 2026-05-31 | 3 | Med
MH25021 JNMC 5th Floor Enabling | AHCA Stage III | Maryann / RDG | Pending | 2026-05-18 | 2026-05-24 | 1 | High
MH25021 JNMC 5th Floor Enabling | Permit/AHJ | Maryann / RDG | Pending | 2026-05-25 | 2026-06-21 | 4 | High
MH25009 NCH Radiology Ultrasound | SD | Camila / RDG | Active | 2026-05-04 | 2026-05-17 | 2 | Med
MH25009 NCH Radiology Ultrasound | DD | Camila / RDG | Pending | 2026-05-11 | 2026-05-24 | 2 | Med
MH25009 NCH Radiology Ultrasound | CD Phase 1 | Camila / RDG | Pending | 2026-05-18 | 2026-05-31 | 2 | Med
MH25009 NCH Radiology Ultrasound | AHCA Stage III #1 | Camila / RDG | Pending | 2026-05-25 | 2026-05-31 | 1 | High
MH25009 NCH Radiology Ultrasound | CD Phase 2 | Camila / RDG | Pending | 2026-06-01 | 2026-06-14 | 2 | Med
MH25009 NCH Radiology Ultrasound | AHCA Stage III #2 | Camila / RDG | Pending | 2026-06-08 | 2026-06-14 | 1 | High
MH25009 NCH Radiology Ultrasound | Permit/AHJ | Camila / RDG | Pending | 2026-06-15 | 2026-07-12 | 4 | High
Legend
Design/CD
AHCA Milestone
Permit/AHJ