## Schedule v4
Platform | Project | RDG Team | Milestones & Due Dates | Action Items / Notes | CA (Construction Admin)
CAD | JNMC 5th Floor Enabling | Katy & Aila | AHCA Stage 2 – May 12, 3:00 PM AHCA Stage 3 (mail-in) – 1 week after Stage 2 | Katy to coordinate AHCA Stage 2 date change. Intent to submit Stage 3 one week after Stage 2. RDG backgrounds start this week; ESI receives backgrounds in 2 weeks. | Add CA phase after permit milestones (OAC, RFIs, submittals, site visits).
REVIT | JNMC 3rd Floor ICU | Rhyna & Yare (Katy) | AHCA Stage 2 – May 14, 1:00 PM AHCA Stage 3 – June 23, 1:00 PM Intermediate Deadline – TBD (Tentative) SD approval – 03-10-26 DD – 05-08-26 CD – 06-17-26 | RDG to send backgrounds to ESI. RDG to send intermediate deadlines to ESI. Tentative dates provided for Arch; ESI to provide coordination drawings 1 week prior to DD & CD deadlines. | Add CA phase after CD/AHCA (bi-weekly CA coordination and field support).
CAD | JWMC CT Scan | Katy & Rhyna (Aila) | ESI Permit Submission (S&S) – March 12 AHCA Stage 3 – April 23, 10:00 AM | Internal Coordination Set submitted. ESI to confirm access panels to RDG. | Add CA phase after permit submission/approval.
CAD | NCH Radiology Expansion | Elizabeth & Maibe | Demo Package: - Internal Coordination – March 9 - 100% S&S Permit – March 16 - AHCA Stage 3 – April 24 New Build-Out: - SD – 04-15-26 - DD – 05-14-26 - CD – 07-10-26 - AHCA Stage III (pending request) | Demo package under development (on-track). New work layout approval in progress pending NCH approval. Site visit to review chases/electrical this week – Date TBD (based on NCH). | Add CA phase after AHCA/permit for construction period support.
CAD | JNMC AHU-2-23 | Katy & Rhyna | Review Coordination Set – Completed | RDG submitted to JHS Arch & M/E sets; pending structural drawings (not ready). ESI to send follow-up email to Rhyna on electrical readings. | Add CA tracking line once permit/construction starts.
CAD | JWMC MRI Chiller | Rhyna & Katy | Permit set uploaded to eBuilder on 02/26/2026 for permit. | Currently pending review by Building Department. | Add CA phase after permit approval.

## Gantt CA
Project | SD | DD | CD | AHCA/Permit | CA
JNMC 5th Floor Enabling | ● | ● | ● | ● | ●
JNMC 3rd Floor ICU | ● | ● | ● | ● | ●
JWMC CT Scan | ● | ● | ● | ● | ●
NCH Radiology Expansion | ● | ● | ● | ● | ●
JNMC AHU-2-23 | ● | ● | ● | ● | ●
JWMC MRI Chiller | ● | ● | ● | ● | ●