## Projects (Jackson+Nicklaus)
Nº Proyecto | Nombre Proyecto | Cliente | PM Cliente | PM RDG | Estatus/Accion | Invoicing | AHCA | Data Faltante
23007 | 23007 NCH Cath Lab # 1 | Nicklaus | Pendiente | Katy | Katy to Report |  | Pendiente | PM cliente
23009-09 | JMH ACC West 5th Floor Renovation PM: Maryann Pando | Jackson | Maryann Pando | Eddy | 2/17/26 Reseaved PO-Temp on Hold |  | Pendiente
23017 | JMH Chilled Water Pumps to Emergency Power | Jackson | Pendiente | Eddy |  | PO open, work never started (potential transfer of funds) | Pendiente | PM cliente, estatus
24009-01 | JHS North Pharmacy USP 797 PM: Maryann Pando | Jackson | Maryann Pando Katy to Report | Katy/Aila | Katy to Report | 1/29/26 Katy/Aila, can we invoice any % on CA | Pendiente
24011 | JHS Express Zone Pneumatic Tube | Jackson | Pendiente | Eddy | Open PO, Permit & CA never started (potential transfer of funds) |  | Pendiente | PM cliente
24012 | JHS Jackson West Roof Ladder | Jackson | Pendiente | Rhyna/Maibe | Rhyna/Maibe to Report | 1/29/26 Rhyna/Maibe can we finish this project so we can invoice | Pendiente | PM cliente
24014 | JHS Perdue-Civil-lift station moratorium pumps | Jackson | Pendiente | Rhyna/Eddy | Rhyna to Report | Paid 100% 11/7/25. | Pendiente | PM cliente
24015 | Jackson North MRI PM Maryann Pando | Jackson | Maryann Pando Rhyna to Report | Rhyna | Rhyna to Report | 01/08/26 Invoice 80% CA. 1/28/26 followed up | Pendiente
24015-01 | Jackson North MRI - ASR #01 | Jackson | Pendiente | Rhyna | Rhyna to Report | 01/08/26 Invoice 80% CA. 2/11/26 followed up | Pendiente | PM cliente
24015-02 | Jackson North MRI - ASR #02 | Jackson | Pendiente | Rhyna/Katy | Rhyna to Report | Fully paid 1/8/26 | Pendiente | PM cliente
24020-01 | Jackson West MRI Chiller PM: Maryann Pando | Jackson | Maryann Pando Rhyna to Report | Rhyna/Katy | Rhyna to Report | 2/2/26 Invoice 100% SD & 100% CD | Pendiente
25005-01 | JHS North 3rd Fl - Evaluation | Jackson | Pendiente | Eddy | Eddy to follow up with Maryann 10-14-25 |  | Pendiente | PM cliente
25012 | JNMC HR Connect | Jackson | Pendiente | Eddy | Eddy to check and confirm final payment. | 75% Invoice sent 10/2/25 100% Invoice sent 11/6/22 | Pendiente | PM cliente
25012-01 | JNMC HR Connect - ASR #01 | Jackson | Pendiente | Eddy | Eddy to check and confirm final payment. | 75% Invoice sent 10/2/25 100% Invoice sent 11/6/22 | Pendiente | PM cliente
25013 | UM SCCC Lab Expansion- MNC 1014 PM: Sancha Foreman | Nicklaus | Sancha Foreman AHCA Stage III on April | Katy/Yare | AHCA Stage III on April, CD to be sent on 02/20 | 2/26/26 invoice 25013 90% CD paid | Stage III
25015 | JWMC CT Room PM: Maryann Pando | Jackson | Maryann Pando Follow up with AHCA for Stage III requested for the week of | Rhyna/Katy | Follow up with AHCA for Stage III requested for the week of 03/09 | 01/08/26 Invoice 100% DD sent . 1/15/26 Revised. 1/28/26 Followed up | Stage III
25015-01 | JWMC CT Room PM: Maryann Pando | Jackson | Maryann Pando ASR | Rhyna/Katy | ASR# 2 sent on 02/06 |  | Pendiente
25017 | JNMC AHU Replacement PM: Maryann Pando | Jackson | Maryann Pando Structural Engineer to go to the site week of | Rhyna | Structural Engineer to go to the site week of 02-09 before completing CDs | 2/9/26 invoice Line 1, 80% Line 2, 75% Line 3, 75% | Pendiente
25018 | JWMC Observation Bed Expansion PM Maryann Pando | Jackson | Maryann Pando AHCA Stage I on February | Katy/Yare | AHCA Stage I on February 18, waiting on meeting with End User to approve SD layout | 2/9/26 Invoice 10% SD. 3/5/26 Paid | Stage I
25019 | JNMC 5th Floor Enabling PM: Maryann Pando | Jackson | Maryann Pando Follow up with Maryann on pending information | Katy/Aila | Follow up with Maryann on pending information | 2/9/26 Invoice 10% SD. Paid 2/18/26 | Pendiente
25021 | NCH Radiology Expansion - Ulrasound PM Camila R. N. de Oliveira | Nicklaus | Camila R. N. de Oliveira AHCA Stage III requested on | Liz/Maibe | AHCA Stage III requested on 02-09-26, SD for next meeting, then release backgrounds to the Engineers | 2/9/26 Invoice 10 % SD | Stage III
26003 | JNMC 3rd Floor ICU PM: Maryann Pando | Jackson | Maryann Pando Site visit performed | Rhyna/Yare | Site visit performed, only access to corridors, coordinate for another site visit to check rooms design | 2/11/26 Invoice 10% SD. Paid 2/18/26 | Pendiente
26004 | JHS JMG Cardio and Population Health PM Maryann Pando-Avdakov | Jackson | Maryann Pando-Avdakov Schematic Design Phase | Liz/Maibe | Schematic Design Phase | 2/16/26 Invoice 10% SD.Paid 2/19/26 | Pendiente
26005 | JNMC Central Sterile | Jackson | Pendiente | ????? | 2/25/26 we got a PO need to schedule this project |  | Pendiente | PM cliente, PM RDG
MH 25019 | JNMC Central Sterile | Jackson | Pendiente | Eddy | 2/25/26 we got a PO need to schedule as a project |  | Pendiente | PM cliente
MH 25022 | JNMC 6th Floor Finish Upgrade | Jackson | Pendiente | Eddy | Proposal sent - pending JHS response |  | Pendiente | PM cliente

## Gantt
Cronograma Gantt (Jackson + Nicklaus)
Nº Proyecto | Nombre Proyecto | PM Cliente | PM RDG | Fase | Estatus | W1 03/10 | W2 03/17 | W3 03/24 | W4 03/31 | W5 04/07 | W6 04/14 | W7 04/21 | W8 04/28 | W9 05/05 | W10 05/12 | W11 05/19 | W12 05/26 | W13 06/02 | W14 06/09 | W15 06/16 | W16 06/23 | W17 06/30 | W18 07/07 | W19 07/14 | W20 07/21 | W21 07/28 | W22 08/04 | W23 08/11 | W24 08/18
23007 | 23007 NCH Cath Lab # 1 | Pendiente | Katy | SD | Katy to Report
DD
CD
Permit/AHJ
23009-09 | JMH ACC West 5th Floor Renovation PM: Maryann Pando | Maryann Pando | Eddy | SD | 2/17/26 Reseaved PO-Temp on Hold
DD
CD
Permit/AHJ
23017 | JMH Chilled Water Pumps to Emergency Power | Pendiente | Eddy | SD
DD
CD
Permit/AHJ
24009-01 | JHS North Pharmacy USP 797 PM: Maryann Pando | Maryann Pando Katy to Report | Katy/Aila | SD | Katy to Report
DD
CD
Permit/AHJ
24011 | JHS Express Zone Pneumatic Tube | Pendiente | Eddy | SD | Open PO, Permit & CA never started (potential transfer of funds)
DD
CD
Permit/AHJ
24012 | JHS Jackson West Roof Ladder | Pendiente | Rhyna/Maibe | SD | Rhyna/Maibe to Report
DD
CD
Permit/AHJ
24014 | JHS Perdue-Civil-lift station moratorium pumps | Pendiente | Rhyna/Eddy | SD | Rhyna to Report
DD
CD
Permit/AHJ
24015 | Jackson North MRI PM Maryann Pando | Maryann Pando Rhyna to Report | Rhyna | SD | Rhyna to Report
DD
CD
Permit/AHJ
24015-01 | Jackson North MRI - ASR #01 | Pendiente | Rhyna | SD | Rhyna to Report
DD
CD
Permit/AHJ
24015-02 | Jackson North MRI - ASR #02 | Pendiente | Rhyna/Katy | SD | Rhyna to Report
DD
CD
Permit/AHJ
24020-01 | Jackson West MRI Chiller PM: Maryann Pando | Maryann Pando Rhyna to Report | Rhyna/Katy | SD | Rhyna to Report
DD
CD
Permit/AHJ
25005-01 | JHS North 3rd Fl - Evaluation | Pendiente | Eddy | SD | Eddy to follow up with Maryann 10-14-25
DD
CD
Permit/AHJ
25012 | JNMC HR Connect | Pendiente | Eddy | SD | Eddy to check and confirm final payment.
DD
CD
Permit/AHJ
25012-01 | JNMC HR Connect - ASR #01 | Pendiente | Eddy | SD | Eddy to check and confirm final payment.
DD
CD
Permit/AHJ
25013 | UM SCCC Lab Expansion- MNC 1014 PM: Sancha Foreman | Sancha Foreman AHCA Stage III on April | Katy/Yare | SD | AHCA Stage III on April, CD to be sent on 02/20
DD
CD
AHCA I/II/III
Permit/AHJ
25015 | JWMC CT Room PM: Maryann Pando | Maryann Pando Follow up with AHCA for Stage III requested for the week of | Rhyna/Katy | SD | Follow up with AHCA for Stage III requested for the week of 03/09
DD
CD
AHCA I/II/III
Permit/AHJ
25015-01 | JWMC CT Room PM: Maryann Pando | Maryann Pando ASR | Rhyna/Katy | SD | ASR# 2 sent on 02/06
DD
CD
Permit/AHJ
25017 | JNMC AHU Replacement PM: Maryann Pando | Maryann Pando Structural Engineer to go to the site week of | Rhyna | SD | Structural Engineer to go to the site week of 02-09 before completing CDs
DD
CD
Permit/AHJ
25018 | JWMC Observation Bed Expansion PM Maryann Pando | Maryann Pando AHCA Stage I on February | Katy/Yare | SD | AHCA Stage I on February 18, waiting on meeting with End User to approve SD layout
DD
CD
AHCA I/II/III
Permit/AHJ
25019 | JNMC 5th Floor Enabling PM: Maryann Pando | Maryann Pando Follow up with Maryann on pending information | Katy/Aila | SD | Follow up with Maryann on pending information
DD
CD
Permit/AHJ
25021 | NCH Radiology Expansion - Ulrasound PM Camila R. N. de Oliveira | Camila R. N. de Oliveira AHCA Stage III requested on | Liz/Maibe | SD | AHCA Stage III requested on 02-09-26, SD for next meeting, then release backgrounds to the Engineers
DD
CD
AHCA I/II/III
Permit/AHJ
26003 | JNMC 3rd Floor ICU PM: Maryann Pando | Maryann Pando Site visit performed | Rhyna/Yare | SD | Site visit performed, only access to corridors, coordinate for another site visit to check rooms design
DD
CD
Permit/AHJ
26004 | JHS JMG Cardio and Population Health PM Maryann Pando-Avdakov | Maryann Pando-Avdakov Schematic Design Phase | Liz/Maibe | SD | Schematic Design Phase
DD
CD
Permit/AHJ
26005 | JNMC Central Sterile | Pendiente | ????? | SD | 2/25/26 we got a PO need to schedule this project
DD
CD
Permit/AHJ
MH 25019 | JNMC Central Sterile | Pendiente | Eddy | SD | 2/25/26 we got a PO need to schedule as a project
DD
CD
Permit/AHJ
MH 25022 | JNMC 6th Floor Finish Upgrade | Pendiente | Eddy | SD | Proposal sent - pending JHS response
DD
CD
Permit/AHJ
Leyenda
Diseño
Hito AHCA
Permiso