## Master Projects
Nº Proyecto | Nombre Proyecto | Cliente | PM Cliente | PM RDG | Estatus/Accion | Invoicing | AHCA | Data Faltante
19015 | MSOP Food Cart - PM Milayne Machado | Otro | Milayne Machado CA ongoing | Liz | CA ongoing | 3/3/26 Invoice 50% CA | Pendiente
21027 | Reyes 7880 S. Highway Melbourne | Otro | Pendiente | Maibe | work on revision to comments |  | Pendiente | PM cliente
21033-01 | MDRSP Design Criteria Package ASR#1 - PM Brian Font | Otro | Brian Font | Liz/Yare | 2/5/26 Final DCP Package was submitted 2/24/26 Add Serv - Cost Estimate submitted 3/3/26 follow on Add Serv PO | 3/3/26 waiting on Add Serv PO to send final Invoice | Pendiente
22005 | JHT West UM 4th Floor Pedia IT Closet | Otro | Pendiente | Eddy | In UM's court |  | Pendiente | PM cliente
23007 | 23007 NCH Cath Lab # 1 | Nicklaus | Pendiente | Katy | Katy to Report |  | Pendiente | PM cliente
23009-09 | JMH ACC West 5th Floor Renovation PM: Maryann Pando | Jackson | Maryann Pando | Eddy | 2/17/26 Reseaved PO-Temp on Hold |  | Pendiente
23012-03 | ACC West 1st Floor | Otro | Pendiente | Eddy | ON HOLD |  | Pendiente | PM cliente
23016 | P. Reyes 16940 SW 276 St. Homestead, FL | Otro | Pendiente | Maibe | Special Inspection Reports and Letters completed |  | Pendiente | PM cliente
23017 | JMH Chilled Water Pumps to Emergency Power | Jackson | Pendiente | Eddy |  | PO open, work never started (potential transfer of funds) | Pendiente | PM cliente, estatus
23018-03 | Miami-Dade Tropical Park - PM Mahe | Otro | Mahe Waiting on client to contact us back about ASR sent on | Katy/Eddy | Waiting on client to contact us back about ASR sent on 11/2025. Naty Soto working on it |  | Pendiente
24002 | UMHC - CTU Renovation Project PM: Jackie Candela | Otro | Jackie Candela Katy to Report | Katy/Aila | Katy to Report | 1/29/26 Katy/Aila, can we invoice any % on CA | Pendiente
24005 | Dr. Botero Dental PM Dr. Botero | Otro | Dr. Botero Katy to Report | Katy/Yare | Katy to Report | 3/4/26 When can we send final invoice | Pendiente
24009-01 | JHS North Pharmacy USP 797 PM: Maryann Pando | Jackson | Maryann Pando Katy to Report | Katy/Aila | Katy to Report | 1/29/26 Katy/Aila, can we invoice any % on CA | Pendiente
24011 | JHS Express Zone Pneumatic Tube | Jackson | Pendiente | Eddy | Open PO, Permit & CA never started (potential transfer of funds) |  | Pendiente | PM cliente
24012 | JHS Jackson West Roof Ladder | Jackson | Pendiente | Rhyna/Maibe | Rhyna/Maibe to Report | 1/29/26 Rhyna/Maibe can we finish this project so we can invoice | Pendiente | PM cliente
24014 | JHS Perdue-Civil-lift station moratorium pumps | Jackson | Pendiente | Rhyna/Eddy | Rhyna to Report | Paid 100% 11/7/25. | Pendiente | PM cliente
24015 | Jackson North MRI PM Maryann Pando | Jackson | Maryann Pando Rhyna to Report | Rhyna | Rhyna to Report | 01/08/26 Invoice 80% CA. 1/28/26 followed up | Pendiente
24015-01 | Jackson North MRI - ASR #01 | Jackson | Pendiente | Rhyna | Rhyna to Report | 01/08/26 Invoice 80% CA. 2/11/26 followed up | Pendiente | PM cliente
24015-02 | Jackson North MRI - ASR #02 | Jackson | Pendiente | Rhyna/Katy | Rhyna to Report | Fully paid 1/8/26 | Pendiente | PM cliente
24016 | UMHC Sylvester 2nd Floor Renovation PM: Jackie Candela | Otro | Jackie Candela Katy to Report | Katy/Aila | Katy to Report | 2/12/26 Invoice 25% CA paid 3/4/26 can we invoice ??%CA | Pendiente
24020-01 | Jackson West MRI Chiller PM: Maryann Pando | Jackson | Maryann Pando Rhyna to Report | Rhyna/Katy | Rhyna to Report | 2/2/26 Invoice 100% SD & 100% CD | Pendiente
24021 | MIA Bld 3030 B-Wing, 2nd Floor Office Ren - PM Valenie Urena | Otro | Valenie Urena | Liz/Maibe | 100% CD Phase was submitte on 02-27-26. | 02-27-26 invoice Task 2C-100%CD | Pendiente
24021-01 | MIA Bld 3030 B-Wing, 2nd Floor Office Ren - PM Valenie Urena | Otro | Valenie Urena | Liz/Maibe | 100% CD Phase was submitte on 02-27-26. | 02-27-26 invoice Additional Service #1 - Task 2C-100%CD | Pendiente
24022 | MIA DC 1933 Mechanical Workshop - PM Valenie Urena | Otro | Valenie Urena Bid | Liz/Maibe | Bid & Award phase will proceed following approval from the Constructibility Department | 02-02-026 It cannot be invoiced until the phase is completed | Pendiente
24023 | UM SCCC Viewray Linac Replacement PM: Angel Diez | Otro | Angel Diez All comments have been addressed | Katy/Yare | All comments have been addressed, CA started | 12/4/25 invoice 24023-07 92% Permit sent. Followed 1/29/26& 2/16/26. 1/30/26 invoice 24023-08 100% Permit sent. Nothing to invoice as of 02-09-26 | Pendiente
24024 | UM SCCC Trilogy Linac Replacement PM: Angel Diez | Otro | Angel Diez All comments have been addressed | Katy/Aila | All comments have been addressed, waiting on Carlos to check on the Structural comment | 2/23/26 Invoice 24024-09 100% Per/Bid paid Nothing to invoice as of 02-09-26 | Pendiente
25001 | NSU Parker Building First Floor Chemistry Lab- PM Carlos Guiovani Caceros | Otro | Carlos Guiovani Caceros CA started on | Liz | CA started on 01-23-26 | 1/29/26 Invoice 100% Bid/Permit & 25% CA. Paid 2/23/26 | Pendiente
25004 | UMSC Registration-Waiting Room & Film Library | Otro | Pendiente | Katy | On hold |  | Pendiente | PM cliente
25005-01 | JHS North 3rd Fl - Evaluation | Jackson | Pendiente | Eddy | Eddy to follow up with Maryann 10-14-25 |  | Pendiente | PM cliente
25006 | MIA TSA New Podium at Checkpoint H - PM Valerie Urena | Otro | Valerie Urena Pending transfer Package | Liz | Pending transfer Package & close out project. | Invoice was sent on 10/22/25. Followed 12/4/25 02-02-26 Task 4 -Bid & award phase can be invoiced. | Pendiente
25007 | 25007 MSMC- Skylake Maximize Seating PM Milayne Machado | Otro | Milayne Machado Last follow up | Liz/Eddy | Last follow up 10-27-25. Project is on hold. | 95% CD invoiced paid 11/14/25 | Pendiente
25009 | MIA EDP-AV-DA081A-R - TSA Magazines PM Valenie Urena | Otro | Valenie Urena | Liz/Maibe | 75% DD submitted on 01-30-26 | 02-02-26 invoce Task 1, Task 2A-30%SD & Task 2B-75%DD. | Pendiente
25010 | 4753 Alton Road | Otro | Pendiente | Maibe | proposal for CD, permit & CA approved | retainer paid 11/10/25 | Pendiente | PM cliente
25011 | Mr. & Mrs Manoy Residence | Otro | Pendiente | Aila | Proposal for CD, permit & CA |  | Pendiente | PM cliente
25012 | JNMC HR Connect | Jackson | Pendiente | Eddy | Eddy to check and confirm final payment. | 75% Invoice sent 10/2/25 100% Invoice sent 11/6/22 | Pendiente | PM cliente
25012-01 | JNMC HR Connect - ASR #01 | Jackson | Pendiente | Eddy | Eddy to check and confirm final payment. | 75% Invoice sent 10/2/25 100% Invoice sent 11/6/22 | Pendiente | PM cliente
25013 | UM SCCC Lab Expansion- MNC 1014 PM: Sancha Foreman | Otro | Sancha Foreman AHCA Stage III on April | Katy/Yare | AHCA Stage III on April, CD to be sent on 02/20 | 2/26/26 invoice 25013 90% CD paid | Stage III
25014 | MIA Protocol & International Affairs Offices PM Valenie Urena | Otro | Valenie Urena | Liz/Maibe | 75% DD was submission on 02-12-26. | Task 2A at 100%SD invoiced 12/16/25. Follow up 1/19/26. follow up 1/28/26 02-12-26 invoice Task 2B-75%DD | Pendiente
25015 | JWMC CT Room PM: Maryann Pando | Jackson | Maryann Pando Follow up with AHCA for Stage III requested for the week of | Rhyna/Katy | Follow up with AHCA for Stage III requested for the week of 03/09 | 01/08/26 Invoice 100% DD sent . 1/15/26 Revised. 1/28/26 Followed up | Pendiente
25015-01 | JWMC CT Room PM: Maryann Pando | Jackson | Maryann Pando ASR | Rhyna/Katy | ASR# 2 sent on 02/06 |  | Pendiente
25016 | PediKidz - Phase 2 - Therapy Expansion PM Roland Pereira | Otro | Roland Pereira Backgrounds sent to consultants | Katy/Yare | Backgrounds sent to consultants 1st week of February, DD / CDs are being developed |  | Pendiente
25017 | JNMC AHU Replacement PM: Maryann Pando | Jackson | Maryann Pando Structural Engineer to go to the site week of | Rhyna | Structural Engineer to go to the site week of 02-09 before completing CDs | 2/9/26 invoice Line 1, 80% Line 2, 75% Line 3, 75% | Pendiente
25018 | JWMC Observation Bed Expansion PM Maryann Pando | Jackson | Maryann Pando AHCA Stage I on February | Katy/Yare | AHCA Stage I on February 18, waiting on meeting with End User to approve SD layout | 2/9/26 Invoice 10% SD. 3/5/26 Paid | Stage I
25019 | JNMC 5th Floor Enabling PM: Maryann Pando | Jackson | Maryann Pando Follow up with Maryann on pending information | Katy/Aila | Follow up with Maryann on pending information | 2/9/26 Invoice 10% SD. Paid 2/18/26 | Pendiente
25020 | MIA FIS Terminal E Generator Replacement Prime BR+A Carlos Jimenez | Otro | Pendiente | Liz/Eddy | Subconsultant agreement was sent onn 12-23-25 |  | Pendiente | PM cliente
25021 | NCH Radiology Expansion - Ulrasound PM Camila R. N. de Oliveira | Nicklaus | Camila R. N. de Oliveira AHCA Stage III requested on | Liz/Maibe | AHCA Stage III requested on 02-09-26, SD for next meeting, then release backgrounds to the Engineers | 2/9/26 Invoice 10 % SD | Stage III
26001 | NSU Alvin Sherman Library-Husman Art Gallery Expansion - PM Mindy Irwin | Otro | Mindy Irwin Pemirt Set was submitted on | Liz/Maibe | Pemirt Set was submitted on 02-27-26 | 01/30/26 Invoice 50% SD. Paid 2/23/26 02/19/26 invoice 100%SD, DD & CD. | Pendiente
26002 | UM BPEI USP800 Pharmacy PM: Angel Diez | Otro | Angel Diez Follow up on structural as-built | Katy/Aila | Follow up on structural as-built, develop 3D for next meeting with shaft routing, keep working on the project | EMERGENCY WE NEED TO INVOICE | Pendiente
26003 | JNMC 3rd Floor ICU PM: Maryann Pando | Jackson | Maryann Pando Site visit performed | Rhyna/Yare | Site visit performed, only access to corridors, coordinate for another site visit to check rooms design | 2/11/26 Invoice 10% SD. Paid 2/18/26 | Pendiente
26004 | JHS JMG Cardio and Population Health PM Maryann Pando-Avdakov | Jackson | Maryann Pando-Avdakov Schematic Design Phase | Liz/Maibe | Schematic Design Phase | 2/16/26 Invoice 10% SD.Paid 2/19/26 | Pendiente
26005 | 26005 UM SCCC Hot Lab Renovation PM Arnaldo Rodriguez | Otro | Arnaldo Rodriguez Katy to Report | Katy/ Ka Chai | Katy to Report |  | Pendiente
26005 | JNMC Central Sterile | Jackson | Pendiente | ????? | 2/25/26 we got a PO need to schedule this project |  | Pendiente | PM cliente
MA 24008 | MIA Marketing & Creative Services Offices PM Valenie Urena | Otro | Valenie Urena The revised proposal was sent on | Liz/Eddy | The revised proposal was sent on 11-20-25. Pending Service Order approval |  | Pendiente
MH 24033 | UM SCCC Hot Lab Renovation | Otro | Pendiente | Katy/Ka Chai | Katy to Report |  | Pendiente | PM cliente
|  | Otro | Pendiente | Marketing & Proposals 2025 |  |  | Pendiente | PM cliente, estatus
MA 25003 | MIA Mechanical & Electrical Room Upgrades Prime BR+A Carlos Jimenez | Otro | Pendiente | Liz/Eddy | Subconsultants - Waiting on selection - Follow up on 11-19-25 Status First Tier stage |  | Pendiente | PM cliente
MA 25004 | MDAD General Construction Inspection Services Prime NOVA | Otro | Pendiente | Liz/Eddy | Subconsultants Selected on 01-14-26 Follow up on 01-20-26 |  | Pendiente | PM cliente
MA 25006 | MIA TSA New Podiums PM Valenie Urena | Otro | Valenie Urena Pending information from the PM for the proposal. | Liz/Eddy | Pending information from the PM for the proposal. |  | Pendiente
MH 25011 | UniVida Pembroke Pines | Otro | Pendiente | Katy | Katy to Report |  | Pendiente | PM cliente
MH 25019 | JNMC Central Sterile | Jackson | Pendiente | Eddy | 2/25/26 we got a PO need to schedule as a project |  | Pendiente | PM cliente
MH 25022 | JNMC 6th Floor Finish Upgrade | Jackson | Pendiente | Eddy | Proposal sent - pending JHS response |  | Pendiente | PM cliente
MH 25025 | UM-MNC1041 CT Replacement to Photon CT Pro Dual Source | Otro | Pendiente | Katy/Eddy | Proposal sent on 01/06/26, Follow up with Jackie |  | Pendiente | PM cliente
MH 25026 | UM-MNC1034-SCCC Replacement of Siemens Luminos RF Scanner | Otro | Pendiente | Katy/Eddy | Proposal sent on 01/06/26, Follow up with Jackie |  | Pendiente | PM cliente
MH 25027 | UM-MNC1040-Relocate Siemens YSIO XR Scanner | Otro | Pendiente | Katy/Eddy | Proposal sent on 01/06/26, Follow up with Jackie |  | Pendiente | PM cliente

## Gantt Ejecutivo
Schedule Ejecutivo (estilo Gantt)
Nº Proyecto | Nombre Proyecto | PM Cliente | PM RDG | Fase | Estatus | W1 03/09 | W2 03/16 | W3 03/23 | W4 03/30 | W5 04/06 | W6 04/13 | W7 04/20 | W8 04/27 | W9 05/04 | W10 05/11 | W11 05/18 | W12 05/25 | W13 06/01 | W14 06/08 | W15 06/15 | W16 06/22 | W17 06/29 | W18 07/06 | W19 07/13 | W20 07/20
25004 | UMSC Registration-Waiting Room & Film Library | Pendiente | Katy | SD | On hold
AHCA I
DD
CD
AHCA III
Permit
MH 25019 | JNMC Central Sterile | Pendiente | Eddy | SD | 2/25/26 we got a PO need to schedule as a project
DD
AHCA II
CD
AHCA III
Permit
25020 | MIA FIS Terminal E Generator Replacement Prime BR+A Carlos Jimenez | Pendiente | Liz/Eddy | SD | Subconsultant agreement was sent onn 12-23-25
DD
AHCA II
CD
AHCA III
Permit
25021 | NCH Radiology Expansion - Ulrasound PM Camila R. N. de Oliveira | Camila R. N. de Oliveira AHCA Stage III requested on | Liz/Maibe | SD | AHCA Stage III requested on 02-09-26, SD for next meeting, then release backgrounds to the Engineers
DD
AHCA II
CD
AHCA III
Permit
25009 | MIA EDP-AV-DA081A-R - TSA Magazines PM Valenie Urena | Valenie Urena | Liz/Maibe | SD | 75% DD submitted on 01-30-26
DD
CD F1
AHCA III-1
CD F2
AHCA III-2
25018 | JWMC Observation Bed Expansion PM Maryann Pando | Maryann Pando AHCA Stage I on February | Katy/Yare | SD | AHCA Stage I on February 18, waiting on meeting with End User to approve SD layout
DD
CD
Permit
25007 | 25007 MSMC- Skylake Maximize Seating PM Milayne Machado | Milayne Machado Last follow up | Liz/Eddy | SD Only | Last follow up 10-27-25. Project is on hold.