## Gantt Updated
Schedule actualizado (estilo inicial + barras Gantt)
Nº Proyecto | Nombre Proyecto | Cliente | PM RDG | Milestones | Notes | SD | DD | CD | CA | W1 03/10 | W2 03/17 | W3 03/24 | W4 03/31 | W5 04/07 | W6 04/14 | W7 04/21 | W8 04/28 | W9 05/05 | W10 05/12 | W11 05/19 | W12 05/26 | W13 06/02 | W14 06/09 | W15 06/16 | W16 06/23 | W17 06/30 | W18 07/07 | W19 07/14 | W20 07/21 | W21 07/28 | W22 08/04 | W23 08/11 | W24 08/18
25019 | JNMC 5th Floor Enabling | Jackson | Katy & Aila | AHCA II 05/12 AHCA III +1wk | Date change in progress; backgrounds start this week; ESI in 2 wks. | ●
●
●
●
25020 | JNMC 3rd Floor ICU | Jackson | Rhyna & Yare | AHCA II 05/14 AHCA III 06/23 | SD 03/10, DD 05/08, CD 06/17; ESI to coordinate interim deadlines. | ●
●
●
●
25004 | JWMC CT Scan | Jackson | Katy & Rhyna | Permit S&S 03/12 AHCA III 04/23 | Coordination set submitted; pending access panel confirmation. | ●
●
●
●
25009 | NCH Radiology Expansion | Nicklaus | Elizabeth & Maibe | Demo Permit 03/16 AHCA III 04/24 SD 04/15 DD 05/14 CD 07/10 | Layout approval pending; site visit for chases/electrical TBD. | ●
●
●
●
25017 | JNMC AHU-2-23 | Jackson | Katy & Rhyna | Coord set reviewed | Pending structural drawings; ESI follow-up on electrical readings. | ●
●
●
●
24020-01 | JWMC MRI Chiller | Jackson | Rhyna & Katy | Uploaded eBuilder 02/26 | Pending Building Department review. | ●
●
●
●
Legend
SD
DD
CD
CA